## IT Support Log
Log ID | Date | Reported By | Description | Resolution | Resolved By
LOG-102 | 2009-11-12 | R. Colston (Clerk) | Renewal screen freezes when printing receipt for Contractor licenses. | T. Whitfield added a delay before print call. Workaround, not root-caused. | T. Whitfield
LOG-215 | 2011-01-20 | County Finance Office | New 15% surcharge for Retail/Food Service per Ordinance 2011-07 needs to be reflected in renewal fees. | T. Whitfield updated sp_calc_renewal_fee to apply 15% increase for types A and B, effective 2011. | T. Whitfield
LOG-441 | 2018-06-04 | R. Colston (Clerk) | Home Occupation Plus businesses (per Ordinance 2016-03) are still being charged the base $50 fee, not reflecting their upgraded designation. | D. Marsh patched w_license_renewal (screen-level calc) to add $25 surcharge for type C renewals from 2018 onward. Did NOT update sp_calc_renewal_fee -- out of scope for this fix per D.M.'s note. | D. Marsh
LOG-478 | 2019-09-02 | R. Colston (Clerk) | Two Home Occupation renewals this month show different fees ($50 and $75) for what looks like the same license type. | D. Marsh looked into it briefly, noted it 'might be the LOG-441 patch' but did not confirm or file a follow-up. No further action logged. | D. Marsh
LOG-503 | 2020-03-15 | J. Pae (IT Support) | D. Marsh has left the county. No handoff documentation on file for recent BLPTS changes. | Noted for future reference. No replacement developer assigned at this time. | J. Pae